## Sheet1
To be filled by continuing member who is handing over | [11 empty] | To be filled by receiving members
Issue # | Branch | What is it? | Priority (if incomplete) | Current State | How to Use It | Can It Be Replicated by the new team? | What’s Missing? | Assigned to which Continuing Member? | Due Date | Link | Notes/Audio Links/Others | Verfied | Status/Degree of Inheritance | Comments
|  | What specific part of the branch is it? |  | Briefly describe the current status of the branch. | Steps on how to use the branch, including tools, scripts, or specific methods. | Yes/No (If no, describe why not) | List missing pieces (code, documentation, resources, etc.) that need to be transferred or clarified. | Name of the person passing the inheritance. | Date by which handover needs to be completed.
1 | 2 | SIFT-BoVW | low | Description: The branch currently focuses on loading images, extracting SIFT descriptors, performing clustering (using MiniBatchKMeans), and visualizing the clustering results. It is operational and successfully loads images from a specific folder, computes descriptors, clusters them, and reduces dimensionality for visualization. The images are also displayed by their respective clusters. | Steps: Image Loading: Use load_images_from_folders(base_folder) to load images from a specified folder. The images are resized to 64x64 for consistency. Feature Extraction: SIFT descriptors are extracted using the extract_features(image) function for each image. Clustering Descriptors: The descriptors from all images are stacked and clustered into 30 clusters using MiniBatchKMeans. The BoVW histograms are created for each image based on the descriptors and the clusters. Image Clustering: The BoVW histograms are further clustered into 10 groups using k-means. Dimensionality Reduction: PCA reduces the feature matrix to 2D for visualization. Visualization: The scatter plot shows the 10 image clusters, and sample images from each cluster are displayed using plot_images_by_cluster(). Tools Used: OpenCV: For loading and processing images. SIFT: For extracting feature descriptors. MiniBatchKMeans: For clustering descriptors. PCA: For dimensionality reduction. Matplotlib: For visualizing clusters and images. | Yes | Missing Components: Documentation: Clearer documentation or comments within the code explaining each function's purpose would help the new team understand the flow better. Dependencies: The new team should ensure that all required libraries (OpenCV, scikit-learn, NumPy, Matplotlib, etc.) are installed. A requirements.txt file listing all the required dependencies is recommended. Configuration: Clarification on how to handle images with different naming conventions. | Mingbo | 2024-10-05 | cnn_clustering/sift_cluster.ipynb · main · Yuyang Han / Japanese Handwriting Analysis · GitLab (anu.edu.au) | Focusing on this branch is not suggested, we found that sift is still not able to find the clear targeted features. | Yes, he explained somebit of it to me | Know that where the code is and how to run on my system, but still need to dive deep into its concept to get it fully understood. | Can explain it to the new members next semester and will try to understand maximum of it during summer vacation
2 | 2 | SIFT-Pad | low | 1. Current State: Description: This branch loads images, extracts SIFT descriptors, and performs descriptor padding to standardize the length of feature vectors instead of using BoVW (Bag of Visual Words). The padded descriptors are then prepared for clustering or further analysis. This method is complete but uses padding rather than clustering to handle variable-length descriptors. | Steps: Image Loading: Images are loaded from the folder and resized to 64x64, similar to the first project. Feature Extraction: SIFT descriptors are extracted from each image using extract_features(image). Padding: Descriptors are padded using the pad_descriptors(descriptors_list) function to match the maximum descriptor length across images, ensuring uniform feature dimensions. Padded Descriptors: The padded descriptors are reshaped into 1D vectors for further processing. Tools Used: OpenCV: For image processing. SIFT: For extracting descriptors. NumPy: For handling padding and reshaping. | Yes | Missing Components: Documentation: As with the first project, better inline comments or function descriptions would aid in the understanding of the process. Dependencies: Ensure the necessary libraries are available in a requirements.txt file. | Mingbo | 2024-10-05 | cnn_clustering/sift_cluster_pad.ipynb · main · Yuyang Han / Japanese Handwriting Analysis · GitLab (anu.edu.au) | Comment: This method significantly improves speed over the BoVW approach by avoiding complex clustering and directly padding descriptors. However, the accuracy is significantly lower compared to the BoVW method, and it is not recommended for high-accuracy tasks. | Yes, he explained somebit of it to me | Know that where the code is and how to run on my system, but still need to dive deep into its concept to get it fully understood. | Can explain it to the new members next semester and will try to understand maximum of it during summer vacation
3 | 2 | Siamese Neural Network | high | 1. Current State: Description: The current project is focused on developing a Siamese Neural Network for handwriting verification, where pairs of images are used to determine whether they belong to the same writer. It consists of a custom dataset loader, a Siamese neural network architecture, and a contrastive loss function. The network has been trained, and inference functionality is also implemented to test the model on new image pairs. | Steps: Dataset Loading: The HandwritingDataset class is used to load images from a directory. It creates pairs of images for same or different writers, with transformations applied. Model Architecture: The SiameseNetwork is defined with convolutional layers to extract features from each image, followed by fully connected layers to produce final embeddings for comparison. Loss Function: The ContrastiveLoss is used to compute the loss based on the distance between the embeddings of the two images. Training: Use the train() function to train the model using the provided dataset with the Adam optimizer. Inference: The inference() function loads a pre-trained model to compare two new images and predict whether they are from the same writer. Testing: Use the test() function to evaluate the model's performance on the test dataset by visualizing the distances between image pairs. Tools Used: PyTorch: For building and training the neural network. OpenCV: For loading and processing images. PIL: For image manipulation. Matplotlib: For visualizing results and distances. | Yes | 4. What’s Missing?: Documentation: More in-line comments explaining the purpose of each function and parameters (like the margin in ContrastiveLoss or pair sampling strategy in HandwritingDataset) would be helpful. Dependencies: A requirements.txt file or a list of libraries used (e.g., PyTorch, Torchvision, PIL, etc.) is needed. From the suggestion of Dr. Mohammad, Triplet loss might be a better way comparing with contrastive loss. | Mingbo | 2024-10-05 | Contrastive_Learning/siamese_nn.py · main · Yuyang Han / Japanese Handwriting Analysis · GitLab (anu.edu.au) | Comment: This method provides a scalable way to compare handwriting using neural networks, especially for cases requiring image-to-image similarity comparison. It benefits from the contrastive learning approach, which is particularly suited for tasks where labeled pairs are available. However, the training process can be time-consuming, and access to high-performance hardware (e.g., GPU) is necessary for efficient training. | Yes, he explained somebit of it to me | Know that where the code is and how to run on my system, but still need to dive deep into its concept to get it fully understood. | Can explain it to the new members next semester and will try to understand maximum of it during summer vacation
4 | 2 | Kana-Kanji Classification | low | Description: The current project involves training and testing a Simple Convolutional Neural Network (CNN) for classifying handwritten characters. The project includes data augmentation, model training, testing, validation, and inference stages. The model distinguishes between two classes of handwritten characters ("Kana" and "Kanji"), and the CNN architecture is designed for image classification tasks. The project is functional, with clear processes for training, testing, and inference. | Steps: Set Seed: The function set_seed() ensures reproducibility by setting seeds for random number generators. Data Preprocessing and Augmentation: Images are loaded and preprocessed using image_preprocessing() and optionally augmented using data_augmentation(). Images are resized to 64x64 grayscale. Dataset Preparation: The dataset() function is used to load the images and prepare the dataset with options for splitting into training and validation sets. Datasets are converted to PyTorch tensors and one-hot encoded. Model Architecture: The SimpleCNN class defines a basic CNN architecture with four convolutional layers followed by three fully connected layers, designed to classify between two classes. Training: The train() function trains the model on the training dataset using the Adam optimizer and calculates loss using the negative log-likelihood loss (NLLLoss). Validation: The validate() function evaluates the model's performance on the validation dataset, computing accuracy and loss. Inference: The inference() function is used to predict class labels ("Kana" or "Kanji") for new images and saves the results to a CSV file. Main Function: The main() function orchestrates the flow for training, validating, or performing inference, depending on user input. Tools Used: PyTorch: For building and training the neural network. OpenCV: For image processing. PIL: For image augmentation. Matplotlib: For plotting results (e.g., test losses). | Yes | Dataset: The paths to datasets (e.g., train_image_dir) need to be clearly shared or provided. It should be noted that the folder structure should include images grouped by class labels. Documentation: More detailed in-line comments explaining key steps, particularly in the main() function, would be helpful. It would also be useful to document the file structure expected for images. Dependencies: A requirements.txt file listing the necessary libraries (e.g., PyTorch, OpenCV, PIL, Matplotlib) should be provided. Visualization: The current implementation saves the test loss plot but could benefit from more frequent visual monitoring during training for real-time feedback. | Mingbo | 2024-10-05 | character_classifying_cnn/Simple_cnn.py · main · Yuyang Han / Japanese Handwriting Analysis · GitLab (anu.edu.au) | Comment: This CNN-based method is straightforward and easy to implement for basic classification tasks. The data augmentation adds variability, which is helpful for improving model generalization. However, the relatively simple CNN architecture may not capture highly complex patterns compared to more advanced models. For small-scale or simple classification problems, this approach is efficient and works well, but for more complex datasets, further improvements might be needed. | Yes, he explained somebit of it to me | Know that where the code is and how to run on my system, but still need to dive deep into its concept to get it fully understood. | Can explain it to the new members next semester and will try to understand maximum of it during summer vacation
5 | 2 | Large chinese character annotated dataset | high | Finished all task for this module. | All data has uploaded into drive | Yes | None | Mingbo | 2024-10-05 | data - Google 云端硬盘 |  | Yes, he explained somebit of it to me | Know that where the code is and how to run on my system, but still need to dive deep into its concept to get it fully understood. | Can explain it to the new members next semester and will try to understand maximum of it during summer vacation