## Sheet1
To be filled by continuing member who is handing over | [11 empty] | To be filled by receiving members
Issue # | Branch | What is it? | Priority (if incomplete) | Current State | How to Use It | Can It Be Replicated by the new team? | What’s Missing? | Assigned to which Continuing Member? | Due Date | Link | Notes/Audio Links/Others | Verfied | Status/Degree of Inheritance | Comments
|  | What specific part of the branch is it? |  | Briefly describe the current status of the branch. | Steps on how to use the branch, including tools, scripts, or specific methods. | Yes/No (If no, describe why not) | List missing pieces (code, documentation, resources, etc.) that need to be transferred or clarified. | Name of the person inheriting the task. | Date by which handover needs to be completed.
1 | 1 & 2 | Word segmentation | Medium | Our two approaches are built based on segmented characters instead of entire leaflet. However, previous student were using an API that is expired | This requires us to find a new model to do word seg. I tried "tesseract" in "OCR/seg" but accuracy is low when image preprocessing is not finished | No, this is a risk that remained unsolved | Missing entire model and researching part to find model | None | Before branch 1 & 2 testing | Issues | Not having highest priority because the material previous tool are already enough for conducting development. (Not enough for testing)
2 | 1 | OCR | Completed | The free model for japanese and chinese piece together to provide us a reliable ancient jap model for OCR. Accuracy already get Sophie's approval. | To use my ocr model, you need to run every cells in "chi+jap_ocr" and download whatever it tolds you to download | Yes, Arslan's laptop can | Everything under control | Arslan | Already finished | Issues | Finished.
3 | 1 | Everything into system | Low | We need to first make it into system so that the final software can include it. As we don't know the details and branch 1 is not complete, this has low priority | Copy code from .ipynb file and paste it into a .py file | Yes, anyone can do this | Need docstring | Student in next semester who are responsible for branch1 | Before merging branches into software | Issues | Can be easily finished but need to finish entire branch before make code into software
4 | 1 | Common appear character filtration | Completed | The algorithm is in "OCR/create_csv". Common appear character are selected by Sophie | To use it, you need to run every cells in "create_csv" and download whatever it tolds you to download | Yes, Arslan's laptop can | Everything under control | Arslan | Already finished | Issues | Finished.
5 | 1 | Common appear character clustering | Completed | Two algorithms are provided in "OCR/common_character_clustering". CoHiClust is suggested by Mohammed | To use it, you need to run every cells in "OCR/common_character_clustering" and download whatever it tolds you to download | Yes, Arslan's laptop can | Mohammed is suggesting we could download and fine-tuning to get higher accuracy (enough though). Moreover, need more tests to determine parameter "max_depth" | Student in next semester who are responsible for branch1 | Already finished but need test | Issues | Finished but could be improve
6 | 1 | Merge multiple character group to cluster whole leaflets. | High | Not yet started. | Find a way to Merge multiple character group to a complete system which do clustering on entire leaflets rather than single character. Abstract explanation: は' + 'か' + 'へ' + 'で' + ...... = entire leaflet clustering! | No, this is a risk that remained unsolved | Bascially everything | Student in next semester who are responsible for branch1 | Before merging branches into software | Issues | Need many test so we need word seg tool
7 | 1 | Testing | Medium | Can't conduct due to word seg tool not exist and image preprocessing is not finished | First get segmented words, then Run "chi+jap_ocr", then "create_csv", then "OCR/common_character_clustering" | Yes, Arslan's laptop can | Data for testing | Student in next semester who are responsible for branch1 | Before merging branches into software | Issues | Need word seg tool
8 | 1 & 2 | Integrate with branch2 | Low | Not yet started. | First determine if leaflets contains enough common_appear character, if so run branch1, else run branch 2 | No, this is a risk that remained unsolved | Bascially everything | Student in next semester who are responsible for branch1 | Before merging branches into software | None | Require comprehensive understanding of branch1 & 2, require 1&2 to be finished
9 | 1 | Further enhance accuarcy of feature extraction | Low | Feature extraction is currently in "OCR/common_character_clustering", it can be further improve by include more algorithms (current doesn't use neural network to extract feature). SIFT tried but poor result | Run every cells in "OCR/common_character_clustering" and download whatever it tolds you to download | Yes, Arslan's laptop can | More feature extraction means higher accuracy | Student in next semester who are responsible for branch1 | Already finished but can be improve. | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/OCR/common_character_clustering.ipynb?ref_type=heads | Not that essential as current algorithms can meet requirements
10 | 1 | Include more common appear character for making branch1 conclusive | Medium | Can't conduct due to word seg tool not exist and image preprocessing is not finished | Run every cells in "OCR/common_character_clustering" and download whatever it tolds you to download | Yes, Arslan's laptop can | More common appear character means branch 1 can include more target images and higher accuracy on determine authors | Student in next semester who are responsible for branch1 | Already finished but can be improve. | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/OCR/common_character_clustering.ipynb?ref_type=heads | Current algorithms can meet requirements. But the more character it include, the better performance entire branch1 have