## Sheet1
To be filled by continuing member who is handing over | [11 empty] | To be filled by receiving members
Issue # | Branch | What is it? | Priority (if incomplete) | Current State | How to Use It | Can It Be Replicated by the new team? | What’s Missing? | Assigned to which Continuing Member? | Due Date | Link | Notes/Audio Links/Others | Verfied | Status/Degree of Inheritance | Comments
|  | What specific part of the branch is it? |  | Briefly describe the current status of the branch. | Steps on how to use the branch, including tools, scripts, or specific methods. | Yes/No (If no, describe why not) | List missing pieces (code, documentation, resources, etc.) that need to be transferred or clarified. | Name of the person passing the inheritance. | Date by which handover needs to be completed.
1 | 1 & 2 | Word segmentation | Medium | Our two approaches are built based on segmented characters instead of entire leaflet. However, previous student were using an API that is expired | This requires us to find a new model to do word seg. I tried "tesseract" in "OCR/seg" but accuracy is low when image preprocessing is not finished | No, this is a risk that remained unsolved | Missing entire model and researching part to find model | Zhishang | Before branch 1 & 2 testing | Issues | Not having highest priority because the material previous tool are already enough for conducting development. (Not enough for testing) | Yes, we are completely aware of this word segmentation task and risk associated with it | Zhishang told us regarding this and about the API that was going to be expired | Next semester, we continuing members will have to figure out how bring up some alternative for the expired software
2 | 1 | OCR | Completed | The free model for japanese and chinese piece together to provide us a reliable ancient jap model for OCR. Accuracy already get Sophie's approval. | To use my ocr model, you need to run every cells in "chi+jap_ocr" and download whatever it tolds you to download | Yes, Arslan's laptop can | Everything under control | Zhishang | Already finished | Issues | Finished. | Yes, we ran this on my(Arslan's) laptop and it worked completely fine | Understood the Japanese and Chinese OCR and it worked completely fine on my system | Next Semester, I can explain this thing to new members and also work myself on this
3 | 1 | Everything into system | Low | We need to first make it into system so that the final software can include it. As we don't know the details and branch 1 is not complete, this has low priority | Copy code from .ipynb file and paste it into a .py file | Yes, anyone can do this | Need docstring | Zhishang | Before merging branches into software | Issues | Can be easily finished but need to finish entire branch before make code into software | Yes, understood what this task meant | Can do it myself or assign to someone else from group member to do this. | This part is easy to manage, so can comfortably do in next semester
4 | 1 | Common appear character filtration | Completed | The algorithm is in "OCR/create_csv". Common appear character are selected by Sophie | To use it, you need to run every cells in "create_csv" and download whatever it tolds you to download | Yes, Arslan's laptop can | Everything under control | Zhishang | Already finished | Issues | Finished. | Yes, understood this one from Zhishang | It runs on my(Arslan's) laptop and this part is already finished | Can explain it to the members in next semester that what this task was all about and what we achieved in this.
5 | 1 | Common appear character clustering | Completed | Two algorithms are provided in "OCR/common_character_clustering". CoHiClust is suggested by Mohammed | To use it, you need to run every cells in "OCR/common_character_clustering" and download whatever it tolds you to download | Yes, Arslan's laptop can | Mohammed is suggesting we could download and fine-tuning to get higher accuracy (enough though). Moreover, need more tests to determine parameter "max_depth" | Zhishang | Already finished but need test | Issues | Finished but could be improve | Yes, understood this one from Zhishang and can continue on improving it next semester | It runs on my(Arslan's) laptop and this part is already finished but need some tests according to Dr Muhammad guidance/suggestion and we can do it in the next semester | Understood this task and can explain and assign it to new members next semester as well.
6 | 1 | Merge multiple character group to cluster whole leaflets. | High | Not yet started. | Find a way to Merge multiple character group to a complete system which do clustering on entire leaflets rather than single character. Abstract explanation: は' + 'か' + 'へ' + 'で' + ...... = entire leaflet clustering! | No, this is a risk that remained unsolved | Bascially everything | Zhishang | Before merging branches into software | Issues | Need many test so we need word seg tool | Yes, Zhishang told me regarding this issue and we will need to find a way/solution to solve this out | This is actually a risk that remains unresolved and will need to figure out it in next semester | I know some background of this issue as explained to me by Zhishang and can work on this in next semester with the new members
7 | 1 | Testing | Medium | Can't conduct due to word seg tool not exist and image preprocessing is not finished | First get segmented words, then Run "chi+jap_ocr", then "create_csv", then "OCR/common_character_clustering" | Yes, Arslan's laptop can | Data for testing | Zhishang | Before merging branches into software | Issues | Need word seg tool | Yes, Zhishang explained me regarding this | It runs on my laptop, but image preprocessing remained unfinished so that's why it couldn't get completed this time, so will have to finish image processing part first and then can continue on this thing. | I know regarding the image preprocessing and this part specifically,so can work on this thing and can also assign it to new members as well.
8 | 1 & 2 | Integrate with branch2 | Low | Not yet started. | First determine if leaflets contains enough common_appear character, if so run branch1, else run branch 2 | No, this is a risk that remained unsolved | Bascially everything | Zhishang | Before merging branches into software | None | Require comprehensive understanding of branch1 & 2, require 1&2 to be finished | Yes, Zhishang told me that Branch 1 isn't merged with Branch 2 yet. | Right now, I don’t have any comprehensive understanding of Branch 1 & Branch 2, but will try to study these branches over the holiday period and will try to initiate this part as well. | This part will require a good understanding of both the branches and both time and effort as well.
9 | 1 | Further enhance accuarcy of feature extraction | Low | Feature extraction is currently in "OCR/common_character_clustering", it can be further improve by include more algorithms (current doesn't use neural network to extract feature). SIFT tried but poor result | Run every cells in "OCR/common_character_clustering" and download whatever it tolds you to download | Yes, Arslan's laptop can | More feature extraction means higher accuracy | Zhishang | Already finished but can be improve. | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/OCR/common_character_clustering.ipynb?ref_type=heads | Not that essential as current algorithms can meet requirements | Yes, understood this task | It runs on my laptop, and it's kind of almost completed but still requires some more improvement. | This is not a high priority task but can complete it after all the vital tasks are finished.
10 | 1 | Include more common appear character for making branch1 conclusive | Medium | Can't conduct due to word seg tool not exist and image preprocessing is not finished | Run every cells in "OCR/common_character_clustering" and download whatever it tolds you to download | Yes, Arslan's laptop can | More common appear character means branch 1 can include more target images and higher accuracy on determine authors | Zhishang | Already finished but can be improve. | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/OCR/common_character_clustering.ipynb?ref_type=heads | Current algorithms can meet requirements. But the more character it include, the better performance entire branch1 have | Yes, understood this task from Zhishang | It runs on my laptop, and it's kind of almost completed but still requires some more improvement. | Can explain it to the members in next semester that what this task is and what we need to improve on this and how.
11 | 1 | There is a cell that require classify_pilot, it is from branch 2 | Completed | People who compile the code in "chi+jap_ocr" will be stopped because they need a classify csv to help OCR. That piece of code is from "Simple_cnn" | Run "Simple_cnn" before run "chi+jap_ocr". | Yes, Arslan's laptop can | Code not connected so that these might be a little bit complex | Zhishang | Already finished but can need to be connected | OCR/Simple_cnn.py · main · Yuyang Han / Japanese Handwriting Analysis · GitLab (anu.edu.au) | Run "Simple_cnn" before run "chi+jap_ocr". | Yes, understood this task from Zhishang | It runs on my laptop, and it's kind of almost completed but still requires some more improvement. | This part is easy to manage, so can comfortably do in next semester