## Sheet1
To be filled by continuing member who is handing over | [11 empty] | To be filled by receiving members
Issue # | Branch | What is it? | Priority (if incomplete) | Current State | How to Use It | Can It Be Replicated by the new team? | What’s Missing? | Assigned to which Continuing Member? | Due Date | Link | Notes/Audio Links/Others | Verfied | Status/Degree of Inheritance | Comments
|  | What specific part of the branch is it? |  | Briefly describe the current status of the branch. | Steps on how to use the branch, including tools, scripts, or specific methods. | Yes/No (If no, describe why not) | List missing pieces (code, documentation, resources, etc.) that need to be transferred or clarified. | Name of the person inheriting the task. | Date by which handover needs to be completed.
1 | 2 | Extracting the font skeleton -- Zhang-Suen |  | Done | Fill in the input and output folder directories according to your needs, and then call the corresponding functions. | Yes | N/A | Muhammad Arslan | 2024-10-04 | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/FontThicknessTool/SkeletonTools.py?ref_type=heads | Able to extract skeletons but can't handle straight lines and intersections very well | Yes, Zhihong told me about this task | Yeah, he highlighted these things to me in repo and gave me a bit overview but I haven't ran it on my system yet, but some modules did worked on my laptop | Can explain it to the new members next semester and we can try to improve it and make it more better in working.
2 | 2 | Extracting the font skeleton -- morphological |  | Done | Fill in the input and output folder directories according to your needs, and then call the corresponding functions. | Yes | N/A | Muhammad Arslan | 2024-10-04 | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/FontThicknessTool/SkeletonTools.py?ref_type=heads | Able to extract skeletons but can't handle straight lines and intersections very well | Yes, Zhihong told me about this task | Yeah, he highlighted these things to me in repo and gave me a bit overview but I haven't ran it on my system yet, but some modules did worked on my laptop | Can explain it to the new members next semester and we can try to improve it and make it more better in working.
3 | 2 | Extracting the font skeleton -- contour |  | Done | Fill in the input and output folder directories according to your needs, and then call the corresponding functions. | Yes | N/A | Muhammad Arslan | 2024-10-04 | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/FontThicknessTool/SkeletonTools.py?ref_type=heads | Extract the contours, not the skeleton | Yes, Zhihong told me about this task and I understood this part as well | Yes, I have understood this part and but need to further test it on my system to get better idea of it | Will need to put some effort in to digest this work and will try to incorporate all the knowledge base I have regarding this issue it to the new members as well
4 | 2 | Manually reduce font thickness using convolution kernel |  | Done | Fill in the input and output folder directories according to your needs, and then call the corresponding functions. | Yes | N/A | Muhammad Arslan | 2024-10-04 | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/FontThicknessTool/thickness.py?ref_type=heads | Able to reduce the thickness of the font but need to manually determine whether it needs to be reduced or not | Yes, Zhihong told me about this task and I understood this part as well | Yes, I have understood this part and but need to further test it on my system to get better idea of it | Will need to put some effort in to digest this work and will try to incorporate all the knowledge base I have regarding this issue it to the new members as well
5 | 2 | Data augmentation (horizontal flip, vertical flip, random zoom) |  | Done | Modify the file directory and run it directly | Yes | N/A | Muhammad Arslan | 2024-10-04 | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/cnn_extract_handwriting_style/DataArgumentation.ipynb | Certain data augmentation methods can be added or deleted on demand. | Yes, Zhihong told me about this task and I understood this part as well | Yes, I have understood this part and but need to further test it on my system to get better idea of it | Will need to put some effort in to digest this work and will try to incorporate all the knowledge base I have regarding this issue it to the new members as well
6 | 2 | Extracting handwriting styles using our own neural network |  | Done | In the catalog of the dataset, different authors are distinguished by different folders and there is no need to label the authors. Subsequently, it is straightforward to train and save the model | Yes | N/A | Muhammad Arslan | 2024-10-04 | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/cnn_extract_handwriting_style/OurModel.ipynb | It can perform well on the test set, but when using the model for feature extraction and clustering the features, the results are poor. It is possible that this is because the dataset is too low quality, currently we are using the original pilot dataset, but now we have a larger dataset. | Yes, Zhihong told me about this task and I understood this part as well | Yes, I have understood this part and but need to further test it on my system to get better idea of it | Will need to put some effort in to digest this work and will try to incorporate all the knowledge base I have regarding this issue it to the new members as well
7 | 2 | Extracting handwriting styles using neural networks in keras (retraining) |  | Done | In the catalog of the dataset, different authors are distinguished by different folders and there is no need to label the authors. Subsequently, it is straightforward to train and save the model | Yes | N/A | Muhammad Arslan | 2024-10-04 | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/cnn_extract_handwriting_style/transferLearning.ipynb | The dataset size is not large enough to support the training of models with too much depth. We are currently using the original pilot dataset, but we now have a larger dataset. | Yes, Zhihong told me about this task and I understood this part as well | Yes, I have understood this part and but need to further test it on my system to get better idea of it | Will need to put some effort in to digest this work and will try to incorporate all the knowledge base I have regarding this issue it to the new members as well
8 | 2 | Extracting handwriting styles using neural networks in keras (transfer learning) |  | Done | In the catalog of the dataset, different authors are distinguished by different folders and there is no need to label the authors. Subsequently, only the last one or two layers of the model are trained and the model is saved | Yes | N/A | Muhammad Arslan | 2024-10-04 | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/cnn_extract_handwriting_style/transferLearning.ipynb | Transfer learning is currently not effective due to too much difference between upstream and downstream tasks. | Yes, Zhihong told me about this task and I understood this part as well | Yes, I have understood this part and but need to further test it on my system to get better idea of it | Will need to put some effort in to digest this work and will try to incorporate all the knowledge base I have regarding this issue it to the new members as well
9 | 2 | Clustering the results extracted from the neural network |  | Done | Modify the model path and run it directly | Yes | N/A | Muhammad Arslan | 2024-10-04 | https://gitlab.cecs.anu.edu.au/u7434576/japanese-handwriting-analysis/-/blob/main/cnn_extract_handwriting_style/clustering.ipynb | The current clustering results are poor, which we judge to be due to the fact that the neural network does not learn the feature of handwriting style, but other noise | Yes, Zhihong told me about this task and I understood this part as well | Yes, I have understood this part and but need to further test it on my system to get better idea of it | Will need to put some effort in to digest this work and will try to incorporate all the knowledge base I have regarding this issue it to the new members as well